## Jira Backlog
Epic | Story ID | Story Title | Description | Priority | Story Points | Assignee | Status
Project Setup | PLANT-1 | Setup Python Environment | Setup venv and install Flask, TensorFlow, OpenCV, NumPy | High | 3 | Backend Dev | To Do
Project Setup | PLANT-2 | Create Flask Structure | Create app.py, templates, static, model folders | High | 2 | Backend Dev | To Do
Project Setup | PLANT-3 | Initialize Git Repo | Setup Git and push to GitHub | Medium | 2 | DevOps | To Do
Dataset | PLANT-4 | Download Dataset | Download and organize PlantVillage dataset | High | 5 | ML Engineer | To Do
Dataset | PLANT-5 | Data Preprocessing | Resize images, normalize and augment data | High | 5 | ML Engineer | To Do
Model Development | PLANT-6 | Load Pretrained Model | Load ResNet50/MobileNetV2 without top layer | High | 5 | ML Engineer | To Do
Model Development | PLANT-7 | Add Custom Layers | Add GAP + Dense + Softmax layer | High | 5 | ML Engineer | To Do
Model Development | PLANT-8 | Train Model | Train model and save best .h5 file | High | 8 | ML Engineer | To Do
Model Development | PLANT-9 | Evaluate Model | Generate accuracy, confusion matrix, loss graph | Medium | 5 | ML Engineer | To Do
Backend | PLANT-10 | Image Upload API | Create POST endpoint for image upload | High | 5 | Backend Dev | To Do
Backend | PLANT-11 | Image Preprocessing Module | Convert uploaded image to model input format | High | 5 | Backend Dev | To Do
Backend | PLANT-12 | Prediction API Integration | Load model and return prediction + confidence | High | 8 | Backend Dev | To Do
Backend | PLANT-13 | Error Handling | Validate file type and handle invalid inputs | Medium | 3 | Backend Dev | To Do
Frontend | PLANT-14 | Create Home Page | Design landing page with project intro | Medium | 3 | Frontend Dev | To Do
Frontend | PLANT-15 | Create Upload Page | Build image upload UI with preview | High | 5 | Frontend Dev | To Do
Frontend | PLANT-16 | Create Result Page | Display disease name, confidence, remedies | High | 5 | Frontend Dev | To Do
Frontend | PLANT-17 | Responsive Design | Make UI mobile responsive | Medium | 5 | Frontend Dev | To Do
Testing | PLANT-18 | Unit Testing | Write unit tests for model and API | High | 5 | QA Engineer | To Do
Testing | PLANT-19 | Integration Testing | Test complete workflow | High | 5 | QA Engineer | To Do
Deployment | PLANT-20 | Prepare requirements.txt | Freeze dependencies for deployment | High | 2 | Backend Dev | To Do
Deployment | PLANT-21 | Deploy Application | Deploy Flask app on cloud platform | High | 8 | DevOps | To Do